CSIS3724 USPMS Project: Comprehensive Review, Critique and Roadmap for Completion

Group 16 — The Architects | University Smart Parking & Permit Management System

I have reviewed the three documents you submitted:

- CSIS3724 Software Engineering Project Brief (2026): The official document establishing what your group must produce, the system's required functionality, and the submission requirements.

- Assignment2_G16.pdf: Your group's UML class diagram for the University Smart Parking & Permit Management System (USPMS).

- Group_16_USPMS_SPMP_DRAFT_Submission.docx: Your group's Software Project Management Plan (SPMP), dated 5 October 2026.

The purpose of this review is not simply to identify missing work. It is to help you understand what the project requires, what your group has already established, where your submissions are strong or weak, what must be corrected, and how to complete the remaining work in a logical order.

I will distinguish between:

- Confirmed requirements: What the official project brief explicitly requires.

- Observed issues: Problems or inconsistencies visible in your submitted documents.

- Recommended improvements: Actions that would strengthen your project.

- Unverified work: Items that may already exist but cannot be confirmed from the three documents provided.

One important limitation: I have not been provided with a separate specification document, a quotation, an hours log, lecturer feedback, or the source code for your prototype. Consequently, I can assess how your existing documents describe these deliverables, but I cannot confirm whether the underlying work has been completed correctly.

PART 1: Understanding the Project as a Whole

1.1 What are you actually required to produce?

Before deciding what to do next, you need to understand that this is not simply a programming assignment.

The official project brief requires your group to develop a software engineering project for the University of the Free State. The proposed system must address campus parking problems through a software solution incorporating a user interface, application layer and database. The project must be designed up to the implementation phase.

However, the project also assesses whether you can manage the development process professionally.

Your final project therefore has two interconnected parts.

A. The software system

This is the product your group is designing and developing.

It should address the university's parking challenges through functionality such as:

- Parking permit applications and management.

- Parking zone management.

- Visitor registration and parking reservations.

- Parking availability information.

- Notifications and alerts.

- Parking violations and fines.

- Appropriate access for different user roles.

These are among the capabilities described in the official project brief. Your group has also expanded its working scope in the SPMP to include digital wallet functionality, accessibility parking support, smart parking guidance and additional supporting functions. Any such expansion should remain consistent with the approved specification and the minimum requirements of the brief.

B. The software engineering documentation

This demonstrates how your group analysed, designed, planned, estimated, developed and evaluated the system.

The project brief establishes seven principal submission obligations.

| No. | Deliverable | What it demonstrates | Status based on the documents provided |
| --- | --- | --- | --- |
| 1 | Record of hours spent | How much time the team actually spent on the project and how that time was distributed | An estimate of actual hours appears in the SPMP, but the underlying hours record was not provided. |
| 2 | Specification document | What the client requires the system to do, supported by appropriate UML | A class diagram was provided, but the complete specification was not. |
| 3 | Software Project Management Plan | How the project will be organised, scheduled, estimated and controlled | A substantial SPMP draft was provided. |
| 4 | Quotation | The estimated cost of developing the complete system | The SPMP contains a calculation, but a separate quotation was not provided. |
| 5 | Overview of development effort | How the Iterative-and-Incremental Model was applied and what the team learned | The SPMP explains the intended iterations, but a final retrospective was not provided. |
| 6 | Design documentation | The object-oriented design of the business layer, technology choices and relevant supporting explanations | The class diagram provides an initial foundation, but the required detailed design documentation was not provided. |
| 7 | General submission requirements | Correct formatting, team details, document control and final portfolio assembly | Some requirements are visible in the SPMP; the final portfolio was not provided for review. |

These obligations are explicitly described across the official brief's submission requirements.

The most important conclusion is that your UML class diagram and SPMP are not the entire project. They are two components of a larger collection of interdependent deliverables.

Your next step is to establish a reliable baseline for every deliverable and identify what evidence exists for each one.

PART 2: Critique of Submission 1 — UML Class Diagram

2.1 What your class diagram is trying to achieve

Your submitted diagram identifies a number of classes representing the business domain of the parking system.

These include:

- User

- Vehicle

- ParkingPermit

- PermitApplication

- ParkingZone

- ParkingAvailability

- ParkingReservation

- Visitor

- VisitorPermit

- ParkingViolation

- ParkingFine

- Payment

- PaymentGateway

- ParkingAdministrator

- ProtectionServicesOfficer

- Notification

- SupportRequest

The diagram also defines attributes, operations and relationships between classes. For example, ParkingPermit has attributes such as permitId, permitNumber, permitType and expiryDate, together with operations for activating, renewing, suspending and revoking permits.

This is a reasonable starting point because the system's business domain involves identifiable entities, their information, their responsibilities and their relationships.

However, identifying classes is only the first step in producing a strong object-oriented design.

You must also demonstrate that the classes represent the approved requirements accurately and that their relationships, responsibilities and operations are logically consistent.

2.2 What your group has done well

Strength 1: You have identified the main business entities

Your diagram distinguishes between different concepts rather than treating the entire system as one large object.

For example:

- A PermitApplication represents a request for a permit.

- A ParkingPermit represents the permit itself.

- A ParkingZone represents an area with its own parking characteristics.

- A ParkingViolation records a potential parking offence.

- A ParkingFine represents the financial consequence of a violation.

- A Payment records a payment transaction.

This separation is valuable because these concepts have different responsibilities and lifecycles.

Consider the difference between a permit application and an issued permit.

A student might submit an application on Monday. The administrator might approve it on Wednesday. The permit could then become active and eventually expire.

If your group combined the application and permit into one class without clearly distinguishing their states, it would become harder to represent the application process correctly.

Your separate PermitApplication and ParkingPermit classes provide a foundation for handling this distinction.

What to improve: Make sure the distinction is reflected consistently in your attributes, operations, relationships and state transitions.

Strength 2: You have included multiplicities in your associations

Your diagram includes relationship labels and multiplicities such as 1, 0..* and 0..1.

These express the number of instances that may participate in a relationship.

For example:

- 1 means exactly one.

- 0..1 means zero or one.

- 0..* means zero or many.

- 1..* means one or many.

This is important because the system must distinguish between relationships such as one user owning multiple vehicles and a permit being associated with a particular application.

However, the presence of multiplicities is not sufficient by itself. You must verify that the numbers are placed at the correct ends of each association and that they represent the intended business rules.

Strength 3: You have included operations, not only attributes

Your diagram includes operations such as:

- submitApplication()

- checkValidity()

- cancelReservation()

- calculateAvailability()

- recordViolation()

- issueFine()

- processPayment()

This helps show what the objects are expected to do.

For example, a ParkingReservation should be able to check whether a reservation conflicts with another reservation.

However, you must decide whether every operation belongs to the class in which it currently appears. You must also define the important inputs, outputs and rules associated with the operations.

Strength 4: The diagram addresses several major parking workflows

Your model covers permits, visitors, zones, reservations, availability, violations, fines, payments and notifications.

These concepts are relevant to the problems identified in the official brief.

Nevertheless, the class diagram needs further alignment with the complete approved specification, particularly because your SPMP describes a broader system than the diagram currently demonstrates.

2.3 Critical weaknesses in the UML class diagram

The following are the main areas I recommend addressing.

Weakness 1: The diagram does not visibly represent the full scope described in the SPMP

Priority: Very high

Your SPMP states that the current specification contains nine detailed UML modules:

- Digital Wallet.

- Permit Management System.

- Smart Parking Guidance.

- Notifications and Alerts.

- Online Fine Payment System.

- Accessibility Parking Support.

- Parking Zone Management.

- Visitor Parking Management.

- Parking Availability and Occupancy Monitoring.

These are listed in Section 3.1.2 of the SPMP.

Your class diagram includes concepts that support several of these modules, but the following are not clearly represented as dedicated business concepts:

| SPMP module | What the class diagram currently shows | What needs to be investigated |
| --- | --- | --- |
| Digital Wallet | Payment | Does the approved specification require a wallet balance, wallet transactions, top-ups or refunds? If so, the diagram needs to represent the relevant business concepts. |
| Permit Management | PermitApplication, ParkingPermit | The basic concepts exist, but their lifecycle and approval relationships need to be validated. |
| Smart Parking Guidance | ParkingZone, ParkingAvailability | These may support guidance, but the diagram does not clearly represent the guidance or recommendation responsibility. |
| Notifications and Alerts | Notification | The class exists, but the events that generate notifications and the intended recipients need clarification. |
| Online Fine Payment | ParkingFine, Payment, PaymentGateway | The basic concepts exist, but the payment workflow and transaction outcomes need to be modelled consistently. |
| Accessibility Parking Support | No clearly identifiable dedicated accessibility concept | Determine how accessibility requirements, authorised spaces and eligibility are represented in the approved specification. |
| Parking Zone Management | ParkingZone | The main entity exists, but capacity, restrictions and authorisation rules need validation. |
| Visitor Parking Management | Visitor, VisitorPermit, ParkingReservation | The basic concepts exist, but visitor registration, bay allocation, reservation cancellation and temporary credentials need to align. |
| Parking Availability and Occupancy Monitoring | ParkingAvailability | The class exists, but occupancy updates, data freshness and the relationship to parking zones require clarification. |

Important: Do not automatically create nine additional classes simply because the SPMP lists nine modules. A module is a grouping of related functionality, whereas a class represents a business concept or responsibility.

Your objective is to demonstrate that the business-layer classes collectively support the approved modules.

Step-by-step correction

- Obtain the latest approved specification.

- Extract all functional requirements and business rules.

- Identify the requirements belonging to each of the nine modules.

- List the classes currently responsible for satisfying those requirements.

- Identify requirements that have no corresponding business class, operation or relationship.

- Determine whether each gap requires a new class, a new operation, a relationship change or simply clearer documentation.

- Update the diagram.

- Review it against the requirements before treating it as final.

For example, if the specification says that the system must determine whether a student is eligible to use an accessibility parking space, ask:

- Where is eligibility represented?

- Which business object checks the eligibility?

- How is authorisation associated with the relevant permit or parking zone?

- What happens if eligibility is rejected?

The answers should be supported by your requirements rather than invented during the diagram revision.

Weakness 2: The diagram needs clearer attribute and operation definitions

Priority: High

Your classes contain attributes, but their data types are generally not specified.

For example, the ParkingPermit class includes:

- permitId

- permitNumber

- permitType

- issueDate

- expiryDate

- permitStatus

A more informative UML representation would specify suitable types, for example:

| Attribute | Possible type | Reason |
| --- | --- | --- |
| permitId | UUID or Integer | Identifies a permit uniquely. |
| permitNumber | String | Permit numbers may contain letters or leading zeros. |
| permitType | PermitType enumeration | Restricts the value to approved permit categories. |
| issueDate | Date | Records the issue date. |
| expiryDate | Date | Records when the permit expires. |
| permitStatus | PermitStatus enumeration | Represents the permitted lifecycle states. |

These are proposed design choices, not types specified by your project brief. Your group must choose and justify the types that suit the approved requirements and chosen technologies.

The same principle applies to operations.

Instead of simply writing:

checkValidity()

a more complete design might express the operation as:

checkValidity(asOf: Date): Boolean

This indicates that the operation accepts a date and returns a Boolean result.

If your actual implementation requires more complicated logic, the operation may need a different signature or a separate design explanation.

What to do

Review every class and check:

- Does every attribute have a suitable type?

- Is the attribute necessary?

- Is it clear what each attribute represents?

- Are important attributes optional or mandatory?

- Does each operation have appropriate parameters and a return type?

- Does the operation belong in this class?

- Are lifecycle states represented consistently?

For complex operations, such as checking reservation conflicts or calculating available capacity, you may need a more detailed design.

The official brief requires detailed design only for complex calculations and algorithms, so you do not need to describe every simple operation at algorithm level.

Weakness 3: Some relationships and multiplicities require validation

Priority: Very high

Your diagram contains numerous relationships, but several deserve closer examination.

Example A: User and Vehicle

The intended relationship appears to be that a user owns or manages vehicles.

A plausible model would be:

User 1 ─── 0..* Vehicle

This would mean that one user may have zero or more vehicles, while each vehicle belongs to exactly one user.

However, this should only be used if that is what your approved business rules require.

If vehicles can be transferred between users, shared, or registered on behalf of another person, the model may need to change.

Example B: PermitApplication and ParkingPermit

Your diagram associates applications with permits.

You need to answer two questions:

- Can an application result in a permit only when it is approved?

- Can an application produce more than one permit over time?

If each application can produce at most one permit, and not every application is approved, a relationship allowing zero or one permit per application may be appropriate.

If the system allows renewals through new applications, however, you must distinguish between an initial application, a renewal request and the existing permit.

Example C: ParkingZone and ParkingAvailability

Your diagram includes a relationship indicating that availability describes a zone.

That is conceptually reasonable, but the multiplicity needs to reflect how occupancy information is stored.

If the system stores only the latest availability state, one zone might have one current availability record.

If it stores historical snapshots, one zone could have many availability records over time.

This decision affects both the UML model and the eventual database design.

Example D: ParkingViolation and ParkingFine

Your diagram associates violations with fines.

The business rules should clarify:

- Can a violation exist without a fine?

- Can one violation result in more than one fine?

- Can a fine be voided?

- Can a fine be adjusted?

- Can a fine be paid in multiple transactions?

These are not merely diagramming questions. They affect the system's business logic and data integrity.

Recommended action: Create a relationship review table before changing the diagram.

| Relationship | Business rule | Required multiplicity | Verified? |
| --- | --- | --- | --- |
| User–Vehicle | One user may register multiple vehicles | To be confirmed | No |
| Application–Permit | An approved application may produce a permit | To be confirmed | No |
| Zone–Availability | A zone has current or historical occupancy information | Depends on design | No |
| Violation–Fine | A confirmed violation may result in a fine | To be confirmed | No |
| Fine–Payment | A fine may be paid through one or more transactions, if supported | To be confirmed | No |

Do not mark these relationships as verified until the team has checked them against the actual specification.

Weakness 4: The diagram does not clearly demonstrate inheritance or other advanced object-oriented relationships

Priority: Medium to high

Your model includes User, ParkingAdministrator and ProtectionServicesOfficer.

These classes may represent distinct entities, or the two staff roles may be specialised types of user.

If administrators and protection services officers share common attributes and behaviours, inheritance may be appropriate.

For example:

User

△

|

-------------------

|                 |

ParkingAdministrator  ProtectionServicesOfficer

This is a conceptual example, not a recommendation to apply inheritance without further analysis.

If the roles simply represent permissions assigned to users, a role-based model may be more appropriate than separate subclasses.

Your group must decide which model best represents the actual requirements.

Also investigate whether any of your relationships would be better represented by:

- Inheritance.

- Composition.

- Aggregation.

- Ordinary association.

Do not add these constructs merely to make the diagram look more advanced. Use them when they communicate a genuine business relationship.

Weakness 5: Some classes may contain responsibilities that need further separation

Priority: Medium

Your ParkingAdministrator class includes operations for reviewing permit applications, managing permits, configuring zone authorisation, arranging visitor parking, managing fines and handling support requests.

That is a broad set of responsibilities.

It might be justified if the class represents an administrative role that coordinates these activities. However, you should examine whether it is being treated as the object that performs every underlying business operation.

For example:

- An administrator may approve a permit application.

- The permit object may enforce its own validity rules.

- A parking zone may enforce or expose its access restrictions.

- A fine may maintain its amount and payment status.

This distinction is important because a user role initiating an action is not necessarily the same thing as the business object responsible for executing the operation.

Apply the same review to ProtectionServicesOfficer.

Ask whether each operation represents:

- An action available to that role.

- A responsibility belonging to a business entity.

- A workflow or service that coordinates several entities.

The answer will help determine whether your business-layer design is appropriately organised.

2.4 The most important UML improvement: Traceability

A class diagram should not exist independently of the requirements.

Your group needs to demonstrate how the requirements are represented in the design.

I recommend creating a traceability matrix like this:

| Requirement ID | Requirement | Related class(es) | Relevant operation or relationship | Verified? |
| --- | --- | --- | --- | --- |
| FR-PER-01 | A user can submit a parking permit application | PermitApplication, User | submitApplication() | To be tested |
| FR-PER-02 | An administrator can approve or reject an application | PermitApplication, ParkingAdministrator | Application review and status update | To be tested |
| FR-PER-03 | The system checks whether a permit is valid | ParkingPermit | checkValidity() | To be tested |
| FR-ZON-01 | Administrators can configure parking zones | ParkingZone, ParkingAdministrator | Zone configuration and access restrictions | To be tested |
| FR-VIS-01 | Visitors can receive temporary parking credentials | Visitor, VisitorPermit | generatePermit() | To be tested |
| FR-AV-01 | The system calculates available parking capacity | ParkingZone, ParkingAvailability | calculateAvailability() | To be tested |
| FR-NOT-01 | The system sends relevant parking notifications | Notification and related business entities | Notification creation and delivery workflow | To be tested |

The IDs above are illustrative. Replace them with the actual requirement IDs from your specification.

How to use this matrix

For every functional requirement:

- Identify the business entity or entities involved.

- Identify the operation responsible for satisfying it.

- Confirm that the required relationship exists.

- Check whether the requirement introduces a special business rule.

- Determine how the requirement will be verified in the eventual system.

- Record any gap and assign someone to resolve it.

This gives you a practical way to check whether your diagram is complete without relying on visual appearance alone.

My overall assessment of Assignment 2

Your class diagram is a useful starting point. It identifies many relevant entities and includes operations and relationships.

However, I would not yet treat it as a final business-layer design.

The most important work is to validate the diagram against the complete approved requirements, clarify multiplicities, define types and operation signatures, and ensure that the design accounts for the full approved scope.

PART 3: Critique of Submission 2 — Software Project Management Plan

Your SPMP is more comprehensive than the class diagram because it addresses the management of the development process, rather than only the structure of the system.

The draft includes sections covering scope, assumptions, deliverables, estimates, development iterations, DevOps, remote working, team organisation, risk management, quality, change control, configuration management, communication, maintenance, security and process improvement.

That is a strong structural foundation.

However, a project management plan must do more than describe good practices. It must establish a realistic, internally consistent and actionable plan for your particular group.

3.1 What your SPMP does well

Strength 1: It recognises the required development model

The official project brief requires the Iterative-and-Incremental Model. Your SPMP explicitly adopts this model and describes five iterations, from initial project framing through to final refinement.

Your proposed iterations are:

- I0 — Inception / Baseline.

- I1 — Core Requirements.

- I2 — Detailed Analysis.

- I3 — Final Prototype Integration.

- I4 — Final Refinement.

This is useful because it provides a logical framework for planning the remaining work.

What needs improvement: The plan should distinguish clearly between iterations already completed, work currently underway and work that remains.

It should also provide evidence that the iterations actually happened, rather than merely describing how they were intended to happen.

Strength 2: It recognises that integration and testing matter

Your SPMP acknowledges that completing individual features is not enough.

It includes integration, regression checking, error-path scenarios, defect management and evidence capture in its later iterations.

This is particularly important for USPMS because the features depend on one another.

For example, a permit application may involve:

- A user submitting an application.

- The application being reviewed.

- A permit being issued.

- The permit being associated with a vehicle or authorised parking zone.

- The permit's validity being checked during a compliance workflow.

Testing these steps independently would not establish that the complete workflow functions correctly.

Your plan correctly identifies integration and verification as priorities.

Strength 3: It includes risk management

The SPMP identifies 12 risks, including scope creep, ambiguous parking rules, remote collaboration problems, unavailable external integrations, authorisation failures, inconsistent occupancy information and submission problems.

These risks are relevant to your project.

The inclusion of risk owners and triggers is particularly useful because it allows the team to decide who must respond when a problem arises.

What needs improvement: The risks should be reviewed against the actual current state of the project, and each major risk should have a clear response, deadline or review point.

Strength 4: It takes blended and remote working seriously

The brief explicitly requires an SPMP that explains how the development team will be supported while working from home, online and face-to-face.

Your plan addresses communication channels, shared repositories, handovers, availability expectations and backup procedures.

That is appropriate for a group project in which members may work at different times or in different locations.

Strength 5: It establishes a useful quality framework

Your SPMP includes a Definition of Done that requires implementation or documentation, checks, evidence, no unresolved critical defect and consistency between requirements, design and implementation.

This is one of the most useful sections of the draft.

You should preserve this principle and apply it to the remaining deliverables.

A document is not complete merely because someone has typed it. It must be reviewed, aligned with the project baseline and ready for submission.

3.2 Critical weakness: The team size is inconsistent

Priority: Critical

This is the clearest numerical inconsistency in the SPMP.

The team table lists six named members:

- Ashley Ashirai Hlatshwayo.

- Anelisa Luxolo Rasi.

- Oratile Thuto Moletsane.

- Katlego Motala.

- Kamogelo Andrew Marumo.

- Iviwe Faye.

The table then includes a general entry for the team as a whole in the software development and integration role.

However, the SPMP repeatedly describes a seven-member team and calculates actual hours using seven members working three hours per week over six weekly periods.

The arithmetic is:

7×3×6=126 person-hours

That calculation is correct if seven people actually worked those hours.

However, if only the six named members worked three hours per week for six weeks, the calculation would be:

6×3×6=108 person-hours

The difference is:

126-108=18 person-hours

This does not establish that the reported 126 hours are wrong. Members may have worked different hours, and the team could have a seventh member who was omitted from the table.

But the discrepancy must be resolved before the final submission.

How to correct it

- Confirm the actual number of registered group members.

- Check the official group allocation or the team's records.

- Obtain each member's actual hours.

- Calculate the total from the individual records.

- Reconcile the total with the SPMP's 126-hour figure.

- Correct the team table or the hours calculations.

- Update every section that refers to the team size or actual hours.

Do not change the number to six or seven merely to make the documents agree. Establish the correct figure from the evidence.

3.3 The hours estimate needs a clearer supporting schedule

Your SPMP allocates 300 planned person-hours across five categories.

| Work category | Planned hours | Reported actual hours | Remaining planned hours |
| --- | --- | --- | --- |
| Requirements | 40 | 18 | 22 |
| Specification / Analysis | 60 | 36 | 24 |
| Design | 50 | 18 | 32 |
| Implementation | 120 | 36 | 84 |
| Other | 30 | 18 | 12 |
| Total | 300 | 126 | 174 |

These figures appear in Section 3.4 of your SPMP.

The table is helpful because it distinguishes planned work from reported actual effort.

However, it has two important limitations.

Problem A: The remaining hours are not sufficiently broken down

The table says that 84 implementation hours remain, but it does not establish exactly what those hours will accomplish.

For example, implementation could include:

- Completing permit workflows.

- Implementing visitor reservations.

- Implementing payment handling.

- Connecting the interface to the business layer.

- Integrating the database.

- Fixing defects.

- Running regression checks.

- Preparing the demonstration.

Without a task-level breakdown, the team cannot easily determine whether 84 hours is realistic.

Problem B: The actual hours are not supported by the submitted evidence

The project brief requires a record of the hours actually spent, categorised into requirements, specification/analysis, design, implementation and other work. Documentation, planning, administration and management must also be reflected in those categories.

The SPMP's summary is not a substitute for that underlying record.

What to do next

Create a separate hours register with one entry for each member and work session.

| Date | Team member | Task | Category | Hours | Evidence or outcome |
| --- | --- | --- | --- | --- | --- |
| Actual date | Actual member | Review permit requirements | Requirements | Actual hours | Reviewed requirement records |
| Actual date | Actual member | Refine class diagram | Design | Actual hours | Revised UML file |
| Actual date | Actual member | Implement permit application workflow | Implementation | Actual hours | Commit or working feature |
| Actual date | Actual member | Review documentation | Other | Actual hours | Review notes |

These are examples of the format, not actual work records. Enter the work your team genuinely performed.

At the end of the project:

- Total the hours per member.

- Total the hours per category.

- Calculate the overall actual hours.

- Compare the actual hours with the original estimates.

- Explain substantial differences.

- Submit the completed record with the final portfolio.

Do not backdate invented work or use planned hours as if they were actual hours.

3.4 Your SPMP does not yet establish a sufficiently precise completion schedule

Priority: Very high

Your plan identifies several future milestones, including business-layer design, integrated prototype verification and final portfolio assembly.

However, the schedule does not provide a complete task-by-task calendar showing:

- What must be done.

- Who is responsible.

- When it must be completed.

- How many hours it is expected to take.

- What must be completed first.

- What evidence will establish completion.

This matters because your group needs to coordinate the remaining work without creating conflicts between documentation, implementation and testing.

How to improve the schedule

Create a task register like this:

| Task ID | Task | Owner | Dependency | Estimated hours | Target date | Completion evidence |
| --- | --- | --- | --- | --- | --- | --- |
| T01 | Reconcile approved requirements | Requirements lead | Latest specification | Estimate after review | Set by group | Reviewed requirement baseline |
| T02 | Revise business-layer UML | UML/design team | T01 | Estimate after review | Set by group | Editable, reviewed diagram |
| T03 | Complete object-oriented design | Business analyst and UML team | T02 | Estimate after review | Set by group | Design document |
| T04 | Complete quotation | Cost estimation lead and PM | Agreed estimate baseline | Estimate after review | Set by group | Reconciled quotation |
| T05 | Integrate and verify prototype | Development team | Approved requirements and design | Estimate after review | Set by group | Working workflows and verification evidence |
| T06 | Finalise hours register | All members; PM consolidates | Actual work records | Estimate after review | Set by group | Reconciled hours log |
| T07 | Write development-effort overview | PM and group | Iteration records | Estimate after review | Set by group | Final retrospective |
| T08 | Assemble final portfolio | PM and QA lead | All deliverables | Estimate after review | Official deadline | Complete, validated submission |

The owners and task sequence are proposed allocations. Your group should confirm them and enter actual deadlines from the lecturer's instructions.

Do not estimate every task in isolation. First determine what remains, then estimate each task, identify dependencies and check whether the total fits the team's available time.

3.5 Your SPMP's status and dates need updating

The SPMP identifies itself as a submission-ready draft dated 5 October 2026.

The current date is 10 October 2026.

That means the document should no longer describe 5 October as an upcoming submission date. It should explain the actual status of the project as of the revision date.

The next version should distinguish between:

- Work completed by 5 October.

- Work completed after 5 October.

- Work currently underway.

- Work still outstanding.

- Any milestones or deadlines that have changed.

Also, the phrase "Submission-ready draft" should be reviewed. If this is still a working draft, label it accordingly. If it is being submitted as the final SPMP, remove draft-status wording once the team has completed the appropriate reviews.

This is a documentation-control issue, but it also affects the reliability of your schedule and progress reporting.

3.6 Your SPMP describes intended practices, but their actual use needs evidence

Your DevOps section describes Git/GitHub, branches, issue tracking, code review and continuous integration. It also allows manual quality checks where a full automated pipeline is unavailable.

This is a sensible plan.

However, there is a difference between:

- Saying the team will use version control.

- Demonstrating that the team used version control.

- Providing evidence that the final version can be reproduced.

The same distinction applies to remote meetings, peer reviews, regression checks, risk reviews and iteration retrospectives.

What you should collect

Depending on what your group has actually used, retain:

- Repository history or controlled version records.

- Issue or task tracking records.

- Meeting minutes.

- Requirement and design review notes.

- Iteration review notes.

- Test or verification results.

- Screenshots of working prototype workflows.

- A record of significant changes and the reasons for them.

You do not need to manufacture evidence for every statement in the SPMP. You need to make the final documentation accurately describe what was planned, what was done and what remains incomplete.

3.7 The SPMP's risk management plan needs active use

Your risk register identifies sensible threats, but a risk register is only useful if the team reviews it.

For example, consider the risk of incorrect role authorisation.

A useful response would include:

- Identify the operations that require privileged access.

- Confirm the permitted roles.

- Check that the business logic enforces those permissions.

- Attempt prohibited operations using an unauthorised role.

- Record the results.

- Fix any defects.

- Retest the affected workflows.

The same principle applies to payment failures, stale occupancy information and integration problems.

Your SPMP already anticipates simulated external services and describes fallback behaviour.

The next step is to make sure the prototype and its evidence demonstrate those behaviours where they fall within the approved scope.

PART 4: The Most Important Cross-Document Problem

4.1 Your UML diagram and SPMP need a common project baseline

This is arguably the most important documentation issue after the team-size discrepancy.

Your SPMP describes a system with 35 functional requirements, 15 non-functional requirements, 31 business rules and nine approved UML modules.

However, the submitted class diagram is a single diagram that does not, on its own, demonstrate all those requirements, rules and modules.

That does not automatically mean the diagram is wrong. The complete specification may contain additional diagrams and explanations that were not submitted here.

The problem is that the three documents currently available do not establish a complete, traceable chain from requirements to design to implementation.

You need to build that chain.

What a consistent project should look like

The relationship between your documents should follow this structure:

Official project brief

Defines the minimum system scope and submission requirements.

↓

Approved specification

Defines the detailed functional requirements, non-functional requirements, business rules and required workflows.

↓

UML analysis and business-layer model

Shows the actors, system behaviour, business entities, relationships and relevant state changes.

↓

Object-oriented design

Explains the business objects, their responsibilities, their interactions and their implementation-level structure.

↓

Prototype implementation

Realises the approved functionality.

↓

Verification and evidence

Demonstrates whether the implemented functionality meets the specification.

↓

Final project portfolio

Contains the required documentation, records, quotation and development-effort overview.

The quotation and SPMP support the planning and management of this chain. The hours record documents the effort actually spent on it.

4.2 How to establish consistency

I recommend creating a single master traceability register.

| Requirement ID | Requirement | Specification section | UML reference | Design reference | Prototype evidence | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Actual ID | Permit application | Actual section | Actual use case/class | Actual design section | Screenshot/test/commit | Verified or outstanding |
| Actual ID | Visitor reservation | Actual section | Actual use case/class | Actual design section | Screenshot/test/commit | Verified or outstanding |
| Actual ID | Parking availability | Actual section | Actual use case/class | Actual design section | Screenshot/test/commit | Verified or outstanding |
| Actual ID | Fine payment | Actual section | Actual use case/class | Actual design section | Screenshot/test/commit | Verified or outstanding |
| Actual ID | Permit expiry notification | Actual section | Actual use case/class | Actual design section | Screenshot/test/commit | Verified or outstanding |

The entries above are placeholders, not claims that your prototype has passed these checks.

For each requirement, you should be able to answer:

- Where is the requirement documented?

- Which UML element represents it?

- How is it designed?

- Where is it implemented?

- How is it verified?

- What evidence supports the verification result?

If you cannot answer one of these questions, investigate the gap before declaring the requirement complete.

PART 5: Detailed Roadmap for Completing the Remaining Work

The following roadmap is the order I recommend for your group.

It is organised around dependencies rather than simply following the order in which the project brief lists the deliverables.

The first priority is to establish what is already complete. The second is to finalise the design. The third is to ensure the software and documentation agree. The final priority is to assemble and verify the submission.

Phase 1: Establish the project baseline

Priority: Critical

Objective: Determine the actual state of the project before making further changes.

Step 1.1 — Collect the current authoritative documents

Locate the latest versions of:

- The official project brief.

- The initial specification.

- The revised or final specification.

- All approved UML diagrams.

- The current SPMP.

- The current prototype.

- The quotation, if already prepared.

- The hours register.

- Any lecturer feedback.

- Any marking rubric or final-submission instructions.

Do not assume that the class diagram you uploaded is the only UML artefact your group has produced.

Step 1.2 — Create a deliverables register

For each required deliverable, record its status.

Use four possible states:

- Complete and verified: The deliverable exists, has been reviewed and satisfies its requirements.

- Exists but requires revision: The deliverable exists but contains gaps or inconsistencies.

- In progress: Work has started but is incomplete.

- Not located or not started: The team cannot currently demonstrate that the deliverable is complete.

An example:

| Deliverable | Current assessment | Next action |
| --- | --- | --- |
| Initial specification | Referenced by the SPMP, but not provided here | Locate and preserve it. |
| Final specification | Claimed in the SPMP, but not provided here | Review its contents and obtain the latest approved version. |
| UML class diagram | Provided | Validate and revise against the specification. |
| SPMP | Provided | Correct inconsistencies and update the project status. |
| Quotation | Calculation included in SPMP; separate document not provided | Prepare or locate the required quotation. |
| Design document | Not provided | Locate it or develop it. |
| Prototype | Not provided | Establish the actual implementation status. |
| Hours record | Summary included in SPMP; supporting record not provided | Reconcile actual hours. |
| Development-effort overview | Not provided | Prepare it using iteration evidence. |

Step 1.3 — Resolve contradictions

Before developing more features or producing additional diagrams, resolve:

- The six named team members versus the seven-member references.

- The actual hours versus the hours summary.

- The current project status and dates.

- The authoritative version of the specification.

- Whether the nine-module baseline has actually been approved.

- Whether the implementation matches that baseline.

Deliverable from Phase 1: A verified project status register, a list of discrepancies and an agreed source of truth for the project.

Phase 2: Finalise the specification and UML analysis

Priority: Critical

Objective: Ensure the team has a stable understanding of what the software must do.

The project brief requires a client-style specification using relevant UML techniques and states that lecturer feedback must be incorporated into the final version. The initial and final specifications must both be retained, and the final version must include an appendix briefly listing the changes made.

Step 2.1 — Review the functional requirements

For each functional requirement, check that it is:

- Clearly written.

- Unambiguous.

- Relevant to the approved scope.

- Testable.

- Linked to an appropriate workflow or business rule.

- Consistent with the other requirements.

For example, consider a requirement that an administrator can approve a parking permit application.

You need to know:

- Who can submit an application?

- What information must be provided?

- What validation occurs before submission?

- Who can approve or reject the application?

- What happens after approval?

- What happens after rejection?

- Is a rejection reason recorded?

- Can the applicant view the result?

These questions turn a broad statement into a requirement that can guide design and implementation.

Step 2.2 — Review the non-functional requirements

Your SPMP refers to 15 non-functional requirements, but their individual contents were not provided in the uploaded documents.

Locate them and determine whether each one is measurable or verifiable.

For example, if usability is a requirement, establish how the team will assess it.

If security is a requirement, establish which protected operations must enforce role permissions and how the team will check them.

If maintainability is a requirement, examine whether the business logic is organised into clear responsibilities rather than duplicated across screens.

Avoid replacing the approved non-functional requirements with new ones simply because they sound desirable.

Step 2.3 — Validate the UML diagrams

Use the specification as your source of truth.

Depending on the UML artefacts required by your specification, review the following:

| UML artefact | What it should communicate |
| --- | --- |
| Use case diagram | The system's actors and the functions they interact with. |
| Detailed use cases | Preconditions, main flow, alternative flows and relevant exceptions. |
| Class diagram | Business entities, attributes, operations and relationships. |
| State chart diagrams | The states of a relevant object and the events or conditions that cause transitions. |
| Sequence diagrams, where used | The order of interactions between objects for a particular scenario. |

These artefacts serve different purposes. Do not treat one class diagram as a replacement for every other required form of analysis.

The official brief specifically directs your group to use relevant UML techniques and limits the specification's UML design to the business layer rather than the interface or data-access layers.

Step 2.4 — Record lecturer feedback and changes

For every relevant item of feedback:

- Record the original issue.

- Identify the affected requirement or diagram.

- Decide what change is needed.

- Update the relevant artefact.

- Review the change.

- Add the change to the final specification's appendix.

Do not silently replace the original specification with the revised one.

Deliverable from Phase 2: An approved specification, reviewed UML artefacts and a clear record of changes from the initial version.

Phase 3: Complete the object-oriented design document

Priority: Very high

Objective: Convert your business analysis into a sufficiently detailed object-oriented design.

This is a major deliverable because the official project brief explicitly requires business-layer object-oriented design documentation.

It also requires your design document to identify the technologies selected, state whether the system is online or Windows-based, justify those decisions, and provide a half-page explanation of how the business objects connect to the interface and data-access layers.

Step 3.1 — Define the design document's structure

I recommend the following structure.

1. Introduction

Explain:

- What the design document covers.

- The purpose of the USPMS system.

- The scope of the business-layer design.

- Which approved specification it follows.

2. Design objectives and principles

Explain how your design aims to support:

- Separation of responsibilities.

- Maintainability.

- Data consistency.

- Appropriate access control.

- Reusability where appropriate.

- Consistency with the approved requirements.

3. System architecture

Describe the major layers:

- Presentation or interface layer.

- Business or application layer.

- Data-access layer.

- Database.

- External services or simulated integrations, where applicable.

Your explanation should describe the intended architecture, not imply that an unimplemented component already exists.

4. Business-layer class design

For each important class, document:

- Class name.

- Purpose.

- Attributes and their types.

- Operations and their signatures.

- Relationships with other classes.

- Relevant business rules.

- Important validation behaviour.

You do not need to give every simple method a lengthy algorithmic explanation.

Focus on the complex calculations, validation procedures and workflows that require detailed design.

5. Interaction and workflow design

Explain how important objects cooperate to complete core workflows.

For example, a permit application workflow may involve the applicant, the application, an administrator and the resulting permit.

The design should make clear which object is responsible for each operation.

6. Complex calculations and algorithms

Document the important algorithms required by your approved specification.

Potential candidates, depending on the final requirements, include:

- Checking reservation conflicts.

- Calculating available parking capacity.

- Checking permit validity.

- Determining whether a fine payment has been confirmed.

- Checking authorisation for a parking zone.

For each relevant algorithm, describe:

- Inputs.

- Preconditions.

- Processing steps.

- Business rules.

- Output.

- Error or exceptional conditions.

For example, an availability calculation might begin with a zone's capacity and current occupied spaces.

A simplified calculation is:

Available Spaces=Total Capacity-Occupied Spaces

However, your actual implementation may need to account for reserved bays, restricted spaces, stale occupancy information or other approved rules.

Do not assume that this simple formula is sufficient until you have checked the requirements.

7. Technology choices

Identify your actual selected technologies.

Depending on your implementation, this might cover:

- Programming language.

- Application framework.

- Database technology.

- Development environment.

- Version-control platform.

- Hosting or deployment approach.

For each choice, explain why it is appropriate for the project.

Do not state that the system uses a technology unless the team has actually selected or implemented it.

8. Interface and data-access integration

Provide the required half-page explanation of how the business objects connect with the interface and data-access layers.

For example:

- The interface collects user input and displays results.

- The application or business layer validates requests and applies business rules.

- The data-access layer retrieves and persists information.

- The database stores the relevant records.

- External services are accessed through appropriate integration boundaries.

This should explain how the layers cooperate without unnecessarily expanding the design into a full interface or database design.

9. Design limitations and assumptions

Document relevant limitations, including any simulated services or unavailable integrations.

This is particularly important if the prototype does not use live university authentication, payment processing or physical parking sensors.

Step 3.2 — Improve your class diagram

Use the review in Part 2.

Add suitable types, clarify relationships, validate multiplicities and ensure the classes support the approved requirements.

Step 3.3 — Include supporting diagrams

Include the UML diagrams necessary to explain the design.

For example, sequence diagrams can help demonstrate how a permit application is submitted, reviewed and approved.

State charts can clarify how permits move between states such as pending, active, suspended, expired or revoked, if those states are supported by the approved rules.

Step 3.4 — Review the design against the specification

For every important requirement, confirm that the design shows how it will be satisfied.

Deliverable from Phase 3: A complete, reviewed business-layer design document supported by appropriate UML artefacts.

Phase 4: Complete the quotation and reconcile the cost estimate

Priority: High

Objective: Produce the required quotation using the correct rate and calculation method.

The official project brief specifies:

- R350 per team member per hour.

- General expenses equal to 5% of the total labour amount.

- VAT at 15%.

Your SPMP uses a baseline of 300 planned person-hours and calculates a total project cost of R126,787.50.

Let's verify the calculation.

Step 4.1 — Calculate labour

Labour Cost=Planned Person-Hours×Hourly Rate

Using the SPMP's 300-hour estimate:

300×R350=R105,000

Step 4.2 — Calculate general expenses

General Expenses=Labour Cost×5%
R105,000×0.05=R5,250

Step 4.3 — Calculate the subtotal before VAT

R105,000+R5,250=R110,250

Step 4.4 — Calculate VAT

VAT=R110,250×15%
VAT=R16,537.50

Step 4.5 — Calculate the quotation total

R110,250+R16,537.50=R126,787.50

The arithmetic is correct.

However, the quotation is only as reliable as the estimate used to produce it.

The SPMP currently treats 300 planned person-hours as the full-project baseline, while reporting 126 actual hours through 5 October 2026.

The quotation should therefore be reconciled with the team's current estimate of the remaining work before it is finalised.

Step 4.6 — Prepare the actual quotation document

Your quotation should include:

- Project name.

- Client or intended recipient, using the details appropriate to the assignment.

- Description of the work covered.

- Estimated total person-hours.

- Hourly labour rate.

- Labour subtotal.

- General expenses.

- VAT.

- Total quotation amount.

- Assumptions and relevant limitations.

- Date and version.

You should also clarify whether the quotation reflects the original 300-hour baseline or a formally revised estimate.

Do not silently change the baseline merely because the remaining effort has changed. Retain the original estimate and explain any material revision.

Deliverable from Phase 4: A separate quotation consistent with the SPMP and the official pricing rules.

Phase 5: Verify and complete the working prototype

Priority: Critical if the prototype is incomplete

Objective: Ensure that the implementation supports the approved scope and behaves correctly.

Your SPMP states that a runnable prototype exists and that simulated external services are used where live integrations are unavailable. However, I could not inspect the implementation because the source code or executable was not included in the submitted files.

Therefore, the prototype's actual completion status remains unverified.

Step 5.1 — Establish what currently works

Do not start by rewriting the application.

Instead, identify the current state of each approved module.

| Module | Questions to investigate |
| --- | --- |
| Permit management | Can applications be submitted, reviewed, approved or rejected, and can issued permits be managed? |
| Parking zone management | Can authorised users configure zones, capacities and restrictions? |
| Visitor parking | Can visitors be registered and temporary parking arrangements be created and cancelled? |
| Notifications | Are notifications generated for the relevant events? |
| Parking availability | Can the system calculate and display availability using its actual data source? |
| Fine management | Can violations and fines be recorded and managed? |
| Payment handling | Are payment outcomes represented accurately, including failures or declines? |
| Digital wallet | Does the approved scope require a functioning wallet, and if so, what is implemented? |
| Accessibility support | Are the approved eligibility, access and parking rules represented? |
| Smart parking guidance | Does the system provide the approved guidance behaviour, and what information does it use? |

The precise acceptance criteria should come from your approved specification.

Step 5.2 — Test each workflow from beginning to end

For example, a permit workflow should not be considered complete merely because an application form exists.

Test the complete sequence:

- A user submits an application.

- The system validates the submitted information.

- The application is stored.

- An authorised administrator reviews it.

- The application is approved or rejected.

- The application status is updated.

- If approved, the system creates or activates the appropriate permit.

- The user can view the outcome.

- The system handles invalid or unauthorised actions appropriately.

This is a proposed workflow that must be reconciled with the actual requirements.

Step 5.3 — Test negative and exceptional scenarios

Examples include:

- An application contains invalid information.

- An unauthorised user attempts to approve a permit.

- A permit has expired.

- A reservation conflicts with another reservation.

- Occupancy data is unavailable or stale.

- A payment is declined.

- A visitor reservation is cancelled.

- A notification provider is unavailable.

For each relevant scenario, record:

- Expected result.

- Actual result.

- Pass or fail.

- Defect reference, if applicable.

- Retest result.

Step 5.4 — Integrate the modules

After checking the individual workflows, test how they work together.

For example:

User → Vehicle → Permit Application → Parking Permit → Parking Zone → Compliance Check → Parking Violation → Parking Fine → Payment

Not every workflow needs to follow this exact sequence. The point is to test the relationships that the approved requirements actually define.

Step 5.5 — Capture evidence

For each important workflow, retain suitable evidence.

This might include:

- Screenshots.

- Test results.

- Relevant commits.

- Demonstration records.

- Defect and retest records.

The SPMP already establishes evidence-based completion as a quality principle. Use that principle to determine whether each module is genuinely ready.

Deliverable from Phase 5: An integrated prototype with documented verification results and a clear record of any remaining limitations.

Phase 6: Finalise the SPMP and its supporting management records

Priority: High

Objective: Ensure that the management plan describes the project accurately and provides a realistic plan for the work that remains.

You do not need to rewrite the entire SPMP from scratch. Much of its structure is useful.

Focus on correcting the weaknesses identified in Part 3.

Step 6.1 — Reconcile the team and hours

Correct the team-size inconsistency and verify all actual hours.

Step 6.2 — Update the schedule

Replace vague milestones with a task-level schedule containing:

- Task.

- Owner.

- Dependencies.

- Estimated hours.

- Target date.

- Evidence of completion.

Step 6.3 — Update the iteration status

For each iteration, record:

- Planned objective.

- Actual work completed.

- Artefacts produced.

- Review or feedback received.

- Defects or unresolved issues.

- Changes made.

- Next actions.

Do not mark an iteration complete merely because the calendar period has ended.

Step 6.4 — Review the risk register

For every significant risk, establish whether it is:

- Still relevant.

- More likely than originally expected.

- Already realised.

- Successfully mitigated.

- Requiring additional action.

Assign an owner and a next review point.

Step 6.5 — Confirm the blended working arrangements

The current plan contains useful principles, but the final version should make the arrangements operational.

For example, agree on:

- How frequently the team checks in.

- How meetings are scheduled.

- How members report blockers.

- Where authoritative documents are stored.

- How changes are reviewed.

- How tasks are handed over.

- How unavailable members' responsibilities are covered.

Use arrangements that the team can realistically follow.

Step 6.6 — Review the entire SPMP for consistency

Search for statements that describe the project as already completed when the work is still planned, or statements that use outdated dates or estimates.

Pay particular attention to:

- Project status.

- Team size.

- Hours.

- Remaining effort.

- Module count.

- Prototype status.

- Quotation amount.

- Milestones.

Deliverable from Phase 6: A consistent, current and actionable SPMP that accurately reflects the team's circumstances.

Phase 7: Produce the final overview of development effort

Priority: High

Objective: Explain how your group applied the Iterative-and-Incremental Model in practice.

The official project brief requires a concise description of how the team applied this model and asks what the group would do differently when developing a similar product.

Your SPMP already describes the intended iteration structure. The final overview should explain what actually happened.

Step 7.1 — Describe each iteration

For each iteration, record:

- Its objective.

- The work performed.

- The artefacts produced.

- The feedback received.

- The changes made.

- The problems encountered.

- The resulting improvement to the system.

Step 7.2 — Explain how increments were built

Describe how the system gained functionality over time.

For example, the group may have established the permit model first, added visitor parking later and subsequently integrated notifications or payment handling.

Only use examples that match the team's actual development history.

Step 7.3 — Explain the role of feedback

If feedback resulted in a change to the specification, design or implementation, explain the change and why it was made.

If a change was proposed but not implemented, explain its status.

Step 7.4 — Reflect on what the team would do differently

Avoid vague statements such as "we would communicate better."

Explain the specific improvement and its reason.

For example, if the group discovered that inconsistencies between the UML diagram and implementation created rework, you could explain that you would introduce an earlier integration review and require related documentation to be updated whenever a business rule changes.

That is a concrete lesson because it identifies:

- What happened.

- Why it caused a problem.

- What the team learned.

- What would change next time.

Deliverable from Phase 7: A concise, evidence-based account of the actual development process and lessons learned.

PART 6: Final Portfolio Assembly and Submission Quality

6.1 Compile all required documents

Before final submission, confirm that the portfolio contains the required deliverables.

| Item | Final check |
| --- | --- |
| Initial specification | Original version preserved. |
| Final specification | Approved changes incorporated. |
| Specification change appendix | Changes from the initial version briefly listed. |
| SPMP | Updated and internally consistent. |
| Quotation | Correct calculation and agreed estimate baseline. |
| Design documentation | Business-layer object-oriented design complete. |
| UML diagrams | Editable source files and correctly exported diagrams available. |
| Working prototype | Required workflows demonstrated and limitations documented. |
| Hours register | Actual hours reconciled and categorised correctly. |
| Development-effort overview | Actual iterations and lessons explained. |
| Supporting evidence | Relevant reviews, verification results and changes recorded. |

This checklist is based on the official project requirements, including the retention of both specification versions, the final change appendix, the quotation, the design document, the hours record and the development-effort overview.

6.2 Check the document format

The project brief states that submissions must be Microsoft Word .docx files, with Arial size 10 body text, an appropriate cover page, team information, a table of contents and page numbers. It also requires UML diagrams to be produced using MS Visio or Draw.io.

Before submission, check:

- All required names and student numbers are present.

- The group number is correct.

- The table of contents reflects the final headings.

- Page numbers are correct.

- Diagrams are readable.

- Diagram labels are not clipped.

- The document uses consistent terminology.

- There are no unexplained placeholders.

- The filename follows the lecturer's required convention.

- The final files open correctly.

Your existing SPMP includes a cover page and contents section, but the other documents still need to be checked individually.

6.3 Confirm the final deadline

The uploaded project brief states that the final portfolio deadlines will be provided on Blackboard. The SPMP identifies 5 October 2026 as its own submission date.

Since that date has passed, your group should check the current Blackboard instructions and any lecturer announcements to establish the applicable final submission deadline and whether any milestones have changed.

Do not assume that the SPMP date is the deadline for every remaining deliverable.

PART 7: Recommended Task Allocation for Group 16

Your SPMP already assigns roles to the named team members. I recommend retaining that structure where it remains appropriate, while making individual task ownership explicit.

The following is a proposed allocation based on the roles listed in the SPMP, not a claim that the individuals have agreed to these exact tasks.

| Role | Recommended focus moving forward | Expected output |
| --- | --- | --- |
| Group Leader | Resolve group-level decisions, coordinate with the lecturer where necessary, and help remove major blockers | Decisions and clarified requirements |
| Project Manager / SPMP Coordinator | Maintain the roadmap, schedule, risk register, hours reconciliation and document control | Updated SPMP and progress register |
| Frontend and UI Designer | Verify the interface against the approved workflows and support end-to-end demonstration | Working interface and workflow evidence |
| Requirements Engineer / UML Designer | Review the specification, requirement traceability and UML consistency | Approved requirements and revised UML |
| Business Analyst / UML Designer | Refine business rules, class responsibilities and object-oriented design | Business-layer design document |
| QA, Documentation and Cost Estimation Lead | Coordinate quality reviews, verify document consistency and reconcile the quotation | Verification evidence, final documents and quotation |

The SPMP also identifies software development and integration as a team responsibility. Continue treating integration as a shared responsibility rather than assuming that it belongs to one person alone.

For every task, identify a primary owner and, where necessary, a backup.

The owner should be responsible for producing the deliverable, but another team member should review it before it is treated as complete.

PART 8: Your Immediate Action Plan

The roadmap above explains the entire remaining process. This section translates it into the next actions I would prioritise.

First priority: Resolve the fundamental uncertainties

Complete these before committing to a large amount of new development work.

- Confirm the actual number of group members.

- Reconcile the reported 126 actual person-hours.

- Locate the latest approved specification.

- Locate the initial specification and any lecturer feedback.

- Establish the actual status of the prototype.

- Locate the quotation and hours register, if already prepared.

- Confirm the current final submission deadline.

Why first? These actions establish which work is genuinely missing and prevent your group from duplicating completed work or planning around incorrect assumptions.

Second priority: Finalise the analysis and design

- Review the functional and non-functional requirements.

- Validate the nine-module baseline against the approved scope.

- Revise the class diagram.

- Validate relationships and multiplicities.

- Add suitable attribute types and operation signatures.

- Complete the required business-layer design document.

- Establish traceability between requirements and design.

Why second? The design provides the basis for determining whether the implementation is complete and whether any additional development is necessary.

Third priority: Complete and verify the software

- Identify which required workflows are already implemented.

- Complete any missing mandatory functionality.

- Test each important workflow.

- Test relevant negative and exceptional scenarios.

- Integrate the modules.

- Fix critical defects.

- Capture verification evidence.

Why third? This establishes whether the software satisfies the approved requirements rather than merely appearing to work in isolated demonstrations.

Fourth priority: Finalise management and financial documentation

- Update the SPMP.

- Complete the actual hours register.

- Reconcile the quotation with the estimate.

- Update the schedule and remaining-effort estimates.

- Review the risk register.

- Record the actual iteration history.

- Prepare the final development-effort overview.

Why fourth? These documents should reflect the actual project, not an earlier plan that no longer matches the work.

Fifth priority: Assemble and verify the final portfolio

- Include both the initial and final specification.

- Include the final specification's change appendix.

- Include the final SPMP.

- Include the quotation.

- Include the design documentation.

- Include the hours register.

- Include the development-effort overview.

- Include the required supporting evidence.

- Check formatting and file names.

- Open and inspect every final document.

- Confirm that the complete portfolio satisfies the current Blackboard instructions.

PART 9: Final Evaluation and Strategic Advice

What is the biggest strength of your current submissions?

Your group has already established a substantial conceptual foundation.

The class diagram identifies many of the business entities needed for a parking management system. The SPMP goes further by describing the project scope, development approach, team roles, risks, quality controls, security considerations and iterative delivery process.

These are useful foundations to build on.

What is the biggest weakness?

The main weakness is not necessarily a lack of content. It is the need to establish consistency, completeness and evidence across the project.

Your class diagram, SPMP, specification, implementation and final deliverables must all describe the same system.

At present, the supplied documents reveal several issues that need attention:

- The class diagram does not visibly demonstrate all the modules described in the SPMP.

- Some class definitions and relationships need validation.

- The SPMP contains an unresolved inconsistency between the number of named members and the reported team size.

- The actual hours register has not been provided for verification.

- The schedule needs more precise tasks, dependencies and deadlines.

- The quotation is mathematically correct but still needs to be reconciled with the final estimate and provided as a required deliverable.

- The complete design document and final development-effort overview were not provided for review.

- The prototype's actual implementation and verification status cannot be confirmed from the submitted files.

These are the areas I would address before spending substantial additional effort on optional features or cosmetic improvements.

What should your group avoid doing?

There are four particularly important mistakes to avoid.

First, do not start adding classes or features simply to make the system look more complete. Every addition should be justified by the approved requirements or a formally accepted change.

Second, do not treat documentation and implementation as separate projects. When a requirement or business rule changes, update the relevant UML, design and implementation records.

Third, do not report estimates as actual work. Keep planned hours, actual hours and remaining estimates distinct.

Fourth, do not assume that a document is complete because it has the correct headings. Each section must contain information that is specific to your project and supported by the team's decisions, records or evidence.

Your SPMP already expresses this last principle through its evidence-based Definition of Done. Apply it consistently to the remaining work.

My final recommendation

If I were organising the next stage of this project, I would make the first milestone:

Establish a verified project baseline and a list of outstanding deliverables.

That means confirming the authoritative specification, reconciling the team and hours figures, establishing the prototype's actual status and determining which documents already exist.

Once that is complete, I would move directly into finalising the UML and business-layer design, because those artefacts determine what the software is supposed to do and provide the basis for meaningful implementation verification.

After that, I would concentrate on integration, testing, the remaining management documents and final portfolio assembly.

The guiding principle should be:

Requirements → Analysis and UML → Object-oriented design → Implementation → Verification → Final documentation and submission.

Keep the SPMP, quotation and hours register aligned with that process throughout.

If you follow this order, your group will be in a much stronger position to identify genuine gaps, avoid unnecessary rework and demonstrate that the final USPMS project is not only a functioning software prototype but also a properly planned, designed and documented software engineering project.